Software Life Cycles and Process Models
Prof. McMillan

        Back in the late 1960s software professionals started to see the need for more systematic ways of working[1]. Software projects were frequently late, users were often unhappy with them, code was hard to maintain, and the growing demand for new software loomed as a "software crisis." One of the first steps taken to get a handle on these problems was to define the life cycle of software systems. The concept of a life cycle comes from biology, of course. For example, an insect goes through a series of stages as it plays out the drama of its life: egg, larva, pupa, adult. Once you define the life cycle of an entity, you should be able to better monitor, understand, and control the processes that bring it into existence and shape its characteristics. A process model is one specific prescription for how the life cycle should progress.

        The initial model of the software life cycle (and still the most influential) was the waterfall model. It is an embodiment of managerial common sense, and assumes distinct stages that yield a lot of documentation and require clear approval before being considered complete. One version of the waterfall model:

In the requirements phase, the needs of the client are determined. The client could be the end user, but may be a manager, a marketing department, a business owner, or someone else whose responsibility it is to decide what the software should do. The software engineer helps the client "discover" the requirements in an iterative and highly interactive process. In addition, concerns such as security requirements, portability, cost, and many other details are addressed. The design is the technical blueprint for the system, and is for the developers, testers, maintainers, and others with technical involvement. The goal of design is to spell out the system in enough detail to allow it to be programmed. Implementation is the programming part, of course. It may include testing or other kinds of verification for individual units. Testing is better called verification and validation for reasons that will become clear later in the course. The maintenance phase, which includes correcting errors and various kinds of enhancement over the life of the system, is the one that eventually consumes most resources, as much as 80% of the total effort.

        The waterfall model is a very visible one. That is, managers can monitor it very well, given all the documentation required and clear milestones passed. The trouble with it is that it implies that you can plan the project at the beginning and then move right through to completion with little need to modify anything. (The diagram's feedback arrows are not usually taken very seriously, and are not even shown in some presentations.) For a technically complex system, or in a dynamic environment where needs might change as the project progresses, the waterfall model as usually implemented is unrealistic. It is too rigid, not sufficiently adaptive to unexpected problems and needs. Following this model, many real projects have ground to a halt or yielded an unusable product. If one is creating a system very much like previous ones that the group has created, there may be the knowledge and predictability to justify the waterfall's simple view of the world.

        To get more in touch with reality, Barry Boehm proposed the spiral model. This approach considers risks that might be encountered during the project. A risk is a potential problem, such as finding that an algorithm runs too slowly or that the platform targeted for delivery becomes obsolete. The spiral is just a loop that the developers execute, moving outward toward a final product. With each iteration of the loop, some deliverable is produced. The deliverables can be specific to one project or to one group's practices. They could be the same as the waterfall model's deliverables: requirements documents, design, etc. Often prototypes are created in the spiral model (see below). In each iteration of the spiral model you do the following:

set objectives;
determine alternative ways to meet those objectives;
consider the risks of each alternative;
if all risks are too high then exit the whole project;
choose a course of action;
develop the deliverable;
evaluate the result;

        Another important modification to the waterfall model is to add a prototyping phase. A prototype is a mock-up of a product that allows designers and client to evaluate the design. In software development, prototypes of the user interface are most useful (although one can prototype algorithms, network routines, real-time control, and so on). If a prototyping phase is added to the requirements phase, you can get a good idea of whether you're on track for creating something users really want. You create a prototype in some high-level tool such as an HTML generator, JavaScript, or Toolbook, have users look it over or give it a test spin, and then use the resulting comments to refine the requirements. In today's highly interactive software world, prototyping should be considered mandatory. Some development models such as RAD (rapid application development) really take prototyping to town, making it the heart of the process. Some developers feel that a prototype, being a kludge and a hack, ought to be thrown away before real system development begins. The radicals, though, will take the prototype and keep refining it into the final product. This is sometimes called evolutionary prototyping, as opposed to throw-away prototyping. Whatever kind of prototyping is carried out, it entails some risks. The client, seeing a beautiful user interface, might think the system is almost done when you've hardly started it. Impulsive decisions made for a prototype may get set in concrete, trumping more considered design decisions. In fact, even if you intend to throw the prototype away, you might be pressured to take your ugly kludge and live with its idiosyncrasies forever.

        An incremental model delivers useful system increments to users as they are developed. Design of later increments may be progressing as earlier increments are being deployed (in pipeline fashion). For example, the first increment of a photo editing system may be a picture viewing application. Then we might provide some printing routines. Later still, we might deploy photo editing facilities. Feedback from deployed increments can influence the design of later increments.

        It should be remembered that not all serious software development can be planned very well at all. In a research setting (say in an artificial intelligence or virtual reality lab), software is developed to generate new ideas, test feasibility, and keep a bunch of flighty, egocentric geniuses happy. A lot of innovative ideas come out of such work, and if you're ever a party to it, forget about visibility and management control. Best termed exploratory development, this model will have a sponsor (such as a granting agency), but usually has no direct client. Developers try out different ideas as they occur, building software incrementally, usually in some interactive tool such as Lisp. Guidance comes from theories, developers' conceptual inspirations, and the results of previous experiments. The end product is some proof (or disproof) of concept and a technical publication. No one may actually ever use the software for serious work.

Exercises:

1. List five risks that might exist in the development of a web site connected to a firm's database.
2. For a system that will advise people about new car purchases, list three distinct system increments that could be delivered. Make sure that the system provides useful services after the addition of each increment.
3. In which of the five stages of the waterfall model (as presented above) would each of the following be included?
  1. You run a data file through the system to see if it performs correctly.
  2. The manager of a bowling alley is interviewed to determine what screen layout she wants in the system you are developing to handle bowling shoe rentals.
  3. You add a security feature to a deployed system.
  4. Your team brainstorms about what messages will pass between objects.
  5. Some users try out a crude, quickly-written version of the user interface.
  6. You prove mathematically that a graphics routine you have written is correct.
4. For throw-away prototyping, what would be a good development environment (not listed above)? Explain why.

[1] The late 1960s is when a large number of developers bought into the idea of software engineering. There actually had been some sophisticated discussion of these concepts by the mid-1950s.